## Slide 1
APA Network Call
November 17, 2021

## Slide 2
USCCB Network Arrivals Update
Weekly APA Pipeline Stats | As of 11/10/2021​ | As of 11/17/2021​
Current USCCB APA Capacity​ | 11,030 ind. | 11,030 ind.
Total USCCB APA Individuals Assured​ | 7,295 ind.​ | 9,425 ind. (cumulative)
Total APA Individuals Selected by USCCB, Awaiting Assurance | 3,834 ind. | 1,764 ind.
APA Individuals Traveled to Final Destination​ | 4,045 ind. | 4,957 ind. (45% of capacity)
Total Assured Not Traveled​ | 3,250 ind. | 4,484 ind.
Ready for Departure​ | 1,016 ind. | 1,960 ind.

## Slide 3
Total Number of Evacuees: 84,128
Total Afghan Parolees (including SIV applicants): 69,870
Evacuees at Lily Pads: 2,630
Evacuees at Safe Havens: 46,259
Departures from Safe Havens: 35,252
Total Affiliate Arrivals: 19,314
Total Assurances: 26,319
Total Ready for Departure From Bases: 9,672
APA Statistics

## Slide 4
With almost all cases assured, Refugee Processing Center working on a travel schedule for all APA cases
Safe Haven closures:
  Last group of Afghan nationals departing Fort Lee today
  Fort Bliss and Quantico to be emptied out by 2nd week in December
  Atterbury, Pickett, and Holloman to be emptied out in Dec-Jan
  Fort Dix and Fort McCoy to be emptied out in February
APA Travel Plans

## Slide 5
SSA Updates
PRM has shared that IOM expects to mail the vast majority of outstanding SS cards during the last week of November through the first week of December. If you need urgent receipts of application in the meantime, connect with your local SSA.
Housing on Demand
PRM is working with General Services Administration (GSA) on a program called Housing on Demand. GSA will work to secure extended stay and executive suite type of temporary housing as a last resort to support RA’s. PRM is working with an initial list of 36 cities for this program. USCCB will share details and next steps as soon as we receive them.
APA Award
USCCB’s updated APA award was received today. The full Capacity Development Funding request that was submitted was approved. We will be working over the next few days to get award letters out to all agencies.
Informational Update

## Slide 6
MRIS APA Build
The MRIS team is in the final stages of testing the APA build
Post-arrival transfers
Please reach out to your site’s pre-arrival case manager (PACM) to see if transfer is possible on a case-by-case basis. For walk-in APA cases transfers are allowable if the original assurance agency agrees to the transfer. For non-walk-in cases (e.g., clients who out-migrated during their service period) transfer is unlikely.
Guest Speaker
Ardiane Ademi from Catholic Charities Archdiocese of Galveston-Houston will share about her team’s experience with the APA program and various challenges they’ve worked to overcome over the past few months.
Informational Update

## Slide 7: Catholic Charities of the Archdiocese of Galveston-Houston
Afghan Placement and Assistance Program

## Slide 8: APA Program Overview
Houston Refugee Consortium to resettle 4,000 Afghan Parolees
Support of Senior Management
Resettlement of 124 NYT staff and their families from Kabul Bureau
Staff Structure
  Department has grown from 37 to 65
  Traditional case management adjusted as we work on hiring enough staff
    Teams within the department responsible for different pieces of the APA process (i.e. SAS team helping with SNAP applications, RSI team helping with school registrations, accounting clerks helping with financial distributions, etc.)
    Use of interpreter services for RCA and MG teams
    Organized logistics for airport pick up
Partnership with Extended Stay America
  Catholic Charities office at hotel
  48 hours visit at hotel
  Culturally appropriate food distributions from food pantry twice a week
  Intakes in hotel conference room
  ESL classes in hotel conference room
  Use of Houston Afghan Resettlement Fund
  https://houstonafghanhelp.org
  Partnership with local Afghan Groups and local churches
  Assistance of volunteers
  Assistance of support services of CC in setting up apartments

## Slide 9: Challenges
Retrieval of I-94
Missing documents needed for SNAP applications
Appointments with SSA office
Organizing second dose of vaccinations and school registrations
Staff shortage
Mental health support

## Slide 10
Resources & Training
APA Network Calls - Register here
December 1 (Regularly scheduled USCCB network call December 15)
January 5, 19
February 2, 16
Resources
Staff Mental Health and Secondary Trauma guide
Webinars
Community Sponsorship: Sharing Promising Practices and Lessons Learned
      Thursday, December 2 @3:00pm ET
      Register here

## Slide 11
Thank you!
See you next Wednesday!